## Slide 1
User
Edit profile
Use user information
User
Search
Key-word / name
Coordinates
Address
Sentence
Databases
Results
Store in personal database

## Slide 2
User
Search results
Save a place
Manual input of data
Store in personal database
Troubleshooting
User
Problem while using application
Uses help menu
Administrator
Resolve problem
Uses user database

## Slide 3
Home
Personal
page
My places
Search place
Profile
CouchDB
API 1
API 2
API 3
Administrator
User
Web services
Application / server
Application / client
Help menu

## Slide 4
2017
2018
Today
Nov
Dec
2018
Requirements and design document submitted
11/20/2017
Server-side finished
11/23/2017
Client-side finished
12/5/2017
Final presentation
1/29/2018
20 days
11/1/2017
11/20/2017
Fill-in project information
6 days
11/15/2017
Add screenshots
11/20/2017
2 days
11/21/2017
Database: Add user
11/22/2017
2 days
11/21/2017
Database: Edit user
11/22/2017
2 days
11/21/2017
Database: Delete user
11/22/2017
2 days
11/22/2017
Database: Add place
11/23/2017
2 days
11/22/2017
Database: Edit place
11/23/2017
2 days
11/22/2017
Database: Delete place
11/23/2017
2 days
11/24/2017
Start page: User interface
11/25/2017
2 days
11/24/2017
Start page: Connection to db services
11/25/2017
3 days
11/25/2017
Home: User interface
11/27/2017
3 days
11/25/2017
Home: Connection to db services
11/27/2017
3 days
11/27/2017
My places: User interface
11/29/2017
3 days
11/27/2017
My places: Connection to db services
11/29/2017
4 days
11/29/2017
Search place: User interface
12/2/2017
4 days
11/29/2017
Search place: Connection to db services
12/2/2017
2 days
12/2/2017
Profile: User interface
12/3/2017
2 days
12/2/2017
Profile: Connection to db services
12/3/2017
2 days
12/3/2017
Help menu: User interface
12/4/2017
2 days
12/5/2017
Integrating API 1
12/6/2017
2 days
12/7/2017
Integrating API 2
12/8/2017
2 days
12/9/2017
Integrating API 3
12/10/2017
4 days
12/12/2017
12/15/2017
Testing
4 days
12/16/2017
12/19/2017
Slides
2 days
12/20/2017
Video
12/21/2017
2 days
12/22/2017
Demo
12/23/2017